## Iteration 1
Name | Test Items | Acceptance Test | Preconditions | Input data | Test steps | Expected output | Tester | Result | Comment
Login to new account with Facebook | Authentication | Yes | Logged out of FriendZone Logged out of Facebook There is no user associated with the Facebook account | username: open_pxtezak_user@tfbnw.net password: P@ssword1 | 1. Navigate to login page 2. Click Sign in with Facebook button 3. Enter username and password and submit | You should be logged in | Mike Eskowitz | Passed
Login to existing account with Facebook | Authentication | Yes | Logged out of FriendZone Logged out of Facebook There is a user associated with the Facebook account User has some profile data | username: open_pxtezak_user@tfbnw.net password: P@ssword1 | 1. Navigate to login page 2. Click Sign in with Facebook button 3. Enter username and password and submit 4. Navigate to profile page | You should be logged in. Profile page should have expected data. | Mike Eskowitz | Passed
Add picture to photo album | Album | Yes | Logged in |  | 1. Navigate to photo album page 2. Click the Choose File button 3. Select an image from your file system 4. Click Submit button | The image should appear in your photo album | Cory Stone | Passed | The response after adding an image shows JSON. I've created a new story to update this behavior: https://www.pivotaltracker.com/story/show/141560537
Add info to profile | Profile | Yes | Logged in User has no profile data |  | 1. Navigate to the profile options page 2. Enter data into each of the profile fields. 3. Click Save 4. Reload the page | The profile should be empty when first viewed. The profile data should be persisted when you reload the page. | Ed Orsini | Passed
Edit info in profile | Profile | Yes | Logged in User has existing profile data |  | 1. Navigate to the profile options page 2. Change data in each of the profile fields. 3. Click Save 4. Reload the page | The profile data should be persisted when you reload the page | Ed Orsini | Passed
Remove info from profile | Profile | No | Logged in User has existing profile data |  | 1. Navigate to the profile options page 2. Remove data from each of the profile fields. 3. Click Save 4. Reload the page | The profile data should still be gone when you reload the page | Ed Orsini | Passed
Add first wall post | Wall | Yes | Logged in User has no posts on wall |  | 1. Navigate to the wall page 2. Enter some text into the textbox and click the Post button | The text entered should appear below The email address of the poster should appear with the post | Cory Stone | Passed
Add wall post | Wall | Yes | Logged in User has posts on wall |  | 1. Navigate to the wall page 2. Enter some text into the textbox and click the Post button | The text entered should appear at the top of the wall posts | Cory Stone | Passed
Wall posts have timestamp | Wall | No | Logged in |  | 1. Navigate to the wall page 2. Enter some text into the textbox and click the Post button | In the post that appears on the wall, there should be a timestamp with the current time | Cory Stone | Failed | Timestamp of when post was made is not visible. Created bug: https://www.pivotaltracker.com/story/show/141560713
Wall posts appear in order | Wall | No | Logged in |  | 1. Navigate to the wall page 2. Create multiple posts 3. Reload the page | The posts should appear on the wall in order with the newest posts at the top | Cory Stone | Passed

## Iteration 2
Name | Test Items | Acceptance Test | Preconditions | Input data | Test steps | Expected output | Tester | Result | Comment
Login to new account with Facebook | Authentication | Yes | Logged out of FriendZone Logged out of Facebook There is no user associated with the Facebook account | username: open_pxtezak_user@tfbnw.net password: P@ssword1 Or any real facebook account | 1. Navigate to login page 2. Click Sign in with Facebook button 3. Enter username and password and submit | You should be logged in | Mike Eskowitz | Passed
Login to existing account with Facebook | Authentication | Yes | Logged out of FriendZone Logged out of Facebook There is a user associated with the Facebook account User has some profile data | username: open_pxtezak_user@tfbnw.net password: P@ssword1 Or any real facebook account | 1. Navigate to login page 2. Click Sign in with Facebook button 3. Enter username and password and submit 4. Navigate to profile page | You should be logged in. Profile page should have expected data. | Mike Eskowitz | Passed
Login to new account with Google | Authentication | Yes | Logged out of FriendZone Logged out of Google There is no user associated with the Google account | A google account | 1. Navigate to login page 2. Click Sign in with Google button 3. Enter username and password and submit | You should be logged in | Mike Eskowitz | Passed
Login to existing account with Google | Authentication | Yes | Logged out of FriendZone Logged out of Google There is a user associated with the Google account User has some profile data | A google account | 1. Navigate to login page 2. Click Sign in with Google button 3. Enter username and password and submit 4. Navigate to profile page | You should be logged in. Profile page should have expected data. | Mike Eskowitz | Passed
Add picture to photo album | Album | Yes | Logged in |  | 1. Navigate to photo album page 2. Click the Choose File button 3. Select an image from your file system 4. Click Submit button | The image should appear in your photo album | Mike Eskowitz | Passed
Add info to profile | Profile | Yes | Logged in User has no profile data |  | 1. Navigate to the profile page 2. Click Edit under profile info 3. Enter data into each of the profile fields. 4. Click Save 5. Reload the page | The profile should be empty when first viewed. The profile data should be persisted when you reload the page. | Mike Eskowitz | Passed
Edit info in profile | Profile | Yes | Logged in User has existing profile data |  | 1. Navigate to the profile page 2. Click Edit under profile info 3. Change data in each of the profile fields. 4. Click Save 5. Reload the page | The profile data should be persisted when you reload the page | Mike Eskowitz | Passed
Remove info from profile | Profile | No | Logged in User has existing profile data |  | 1. Navigate to the profile page 2. Click Edit under profile info 3. Remove data from each of the profile fields. 4. Click Save 5. Reload the page | The profile data should still be gone when you reload the page | Mike Eskowitz | Passed
Cancel editing profile | Profile | No | Logged in User has existing profile data |  | 1. Navigate to the profile page 2. Click Edit under profile info 3. Change the data in each of the profile fields 4. Click Cancel | The profile data should be reverted to their original values after clicking cancel | Mike Eskowitz | Passed
View another user's profile | Profile | Yes | Logged in Different user has existing profile data |  | 1. Navigate to another user's profile page | The profile data of the other user should be displayed. The Edit button is not visible. | Cory Stone | Passed
Add first wall post | Wall | Yes | Logged in User has no posts on wall |  | 1. Navigate to the profile page 2. Enter some text into the textbox and click the Post button | The text entered should appear below The email address of the poster should appear with the post | Mike Eskowitz | Passed
Add wall post | Wall | Yes | Logged in User has posts on wall |  | 1. Navigate to the profile page 2. Enter some text into the textbox and click the Post button | The text entered should appear at the top of the wall posts | Mike Eskowitz | Passed | I changed the Preconditions to "User has posts on wall" because it didn't make sense. (It previously said "User has no posts on wall" which would make this redundant with the above test)
Wall posts have timestamp | Wall | No | Logged in |  | 1. Navigate to the profile page 2. Enter some text into the textbox and click the Post button | In the post that appears on the wall, there should be a timestamp with the current time | Mike Eskowitz | Failed | There are no timestamps. See https://www.pivotaltracker.com/story/show/141560713
Wall posts appear in order | Wall | No | Logged in |  | 1. Navigate to the profile page 2. Create multiple posts 3. Reload the page | The posts should appear on the wall in order with the newest posts at the top | Mike Eskowitz | Passed
Add wall post to another wall | Wall | Yes | Logged in |  | 1. Navigate to another user's profile page 2. Enter some text into the textbox and click the Post button | The text entered should appear at the top of the wall posts The logged in user's email address should appear with the post | Cory Stone | Passed
Send friend request | Friends | Yes | Logged in Another user in system who is not friended |  | 1. Navigate to an non-friended user's profile 2. Click Send Friend Request 3. Log in as the non-friended user and view friends list | A friend request with the original user's username should appear on the non-friended user's friends list | Cory Stone | Passed
View friends list | Friends | Yes | Logged in Have multiple friends in the friends list |  | 1. Navigate to the friends list | The friends' usernames and profile pictures should appear in the friends list | Cory Stone | Passed
Remove friend | Friends | No | Logged in Have a friend in the friends list |  | 1. Navigate to the friends list 2. Click the Remove button under a friend | The friend should be removed from the friends list The logged in user should be removed from the friend's friend list | Cory Stone | Failed | Friends are currently only one way, need to make friendship reciprocal in next iteration https://www.pivotaltracker.com/story/show/143273805
Send message to global chat | Chat | No | Logged in |  | 1. Navigate to the chat 2. Send a message to the chat | The message should appear on the left side of the chat window The message should include the user's user ID | Cory Stone | Passed
Receive message in global chat | Chat | No | Logged in as two different users in two separate browsers |  | 1. In both browsers, navigate to the chat 2. In one browser, send a message to the chat | The message should appear on the right side of the chat window in the other browser The message should include the ID of the user who sent it | Cory Stone | Passed

## Iteration 3
Name | Test Items | Acceptance Test | Preconditions | Input data | Test steps | Expected output | Tester | Result | Comment
Login to new account with Facebook | Authentication | Yes | Logged out of FriendZone Logged out of Facebook There is no user associated with the Facebook account | username: open_pxtezak_user@tfbnw.net password: P@ssword1 Or any real facebook account | 1. Navigate to login page 2. Click Sign in with Facebook button 3. Enter username and password and submit | You should be logged in | Cory Stone | Passed
Login to existing account with Facebook | Authentication | Yes | Logged out of FriendZone Logged out of Facebook There is a user associated with the Facebook account User has some profile data | username: open_pxtezak_user@tfbnw.net password: P@ssword1 Or any real facebook account | 1. Navigate to login page 2. Click Sign in with Facebook button 3. Enter username and password and submit 4. Navigate to profile page | You should be logged in. Profile page should have expected data. | Cory Stone | Passed
Login to new account with Google | Authentication | Yes | Logged out of FriendZone Logged out of Google There is no user associated with the Google account | A google account | 1. Navigate to login page 2. Click Sign in with Google button 3. Enter username and password and submit | You should be logged in | Cory Stone | Passed
Login to existing account with Google | Authentication | Yes | Logged out of FriendZone Logged out of Google There is a user associated with the Google account User has some profile data | A google account | 1. Navigate to login page 2. Click Sign in with Google button 3. Enter username and password and submit 4. Navigate to profile page | You should be logged in. Profile page should have expected data. | Cory Stone | Passed
Add picture to photo album | Album | Yes | Logged in |  | 1. Navigate to photo album page 2. Click the Choose File button 3. Select an image from your file system 4. Click Submit button | The image should appear in your photo album | Cory Stone | Passed
Remove picture from photo album | Album | No | Logged in User has an image in the photo album |  | 1. Navigate to photo album 2. Click the Remove button under an image | The image should be removed from your photo album | Cory Stone | Passed
Add unsupported filetype to photo album | Album | No | Logged in | A file with extension that doesn't end in .jpg, .jpeg, .png, or .gif | 1. Navigate to photo album 2. Click the Choose File button 3. Select a file from your file system that does not have one of the supported file formats 4. Click Submit button | You should see an error page indicating that the file was not uploaded | Cory Stone | Passed
Add large image to photo album | Album | No | Logged in | An image larger than 1000000 bytes (~1MB) | 1. Navigate to photo album 2. Click the Choose File button 3. Select n image from your file system that is larger than the supported size limit 4. Click Submit button | You should see an error page indicating that the file was not uploaded | Cory Stone | Passed
Add info to profile | Profile | Yes | Logged in User has no profile data |  | 1. Navigate to the profile page 2. Click Edit under profile info 3. Enter data into each of the profile fields. 4. Click Save 5. Reload the page | The profile should be empty when first viewed. The profile data should be persisted when you reload the page. | Cory Stone | Passed
Edit info in profile | Profile | Yes | Logged in User has existing profile data |  | 1. Navigate to the profile page 2. Click Edit under profile info 3. Change data in each of the profile fields. 4. Click Save 5. Reload the page | The profile data should be persisted when you reload the page | Cory Stone | Passed
Remove info from profile | Profile | No | Logged in User has existing profile data |  | 1. Navigate to the profile page 2. Click Edit under profile info 3. Remove data from each of the profile fields. 4. Click Save 5. Reload the page | The profile data should still be gone when you reload the page | Cory Stone | Passed
Cancel editing profile | Profile | No | Logged in User has existing profile data |  | 1. Navigate to the profile page 2. Click Edit under profile info 3. Change the data in each of the profile fields 4. Click Cancel | The profile data should be reverted to their original values after clicking cancel | Cory Stone | Passed
View another user's profile | Profile | Yes | Logged in Different user has existing profile data |  | 1. Navigate to another user's profile page | The profile data of the other user should be displayed. The Edit button is not visible. | Cory Stone | Passed
Set profile picture | Album, Profile | Yes | Logged in User has an image in the album User has no profile picture set |  | 1. Navigate to your photo album 2. Click on the Profile button under an image 3. Go back to the profile page | The profile should now display the selected image as the profile picture. | Cory Stone | Passed
Change profile picture | Album, Profile | No | Logged in User has multiple images in the album User has a profile picture set |  | 1. Navigate to your photo album 2. Click on the Profile button under an image that is not currently set as the profile picture 3. Go back to the profile page | The profile should now display the selected image as the profile picture. | Cory Stone | Passed
Remove profile picture | Album, Profile | No | Logged in User has a profile picture set |  | 1. Navigate to your photo album 2. Click on the Remove button under the image that is currently set as the profile picture 3. Go back to the profile page | The profile should now display the default profile picture | Cory Stone | Failed | Even the the image is removed from the photo album, it still appears as the user's profile picture. See https://www.pivotaltracker.com/story/show/144492669
Add first wall post | Wall | Yes | Logged in User has no posts on wall |  | 1. Navigate to the profile page 2. Enter some text into the textbox and click the Post button | The text entered should appear below The profile picture and first name of the poster should appear with the post, and should link back to the poster's profile | Cory Stone | Passed
Add wall post | Wall | Yes | Logged in User has posts on wall |  | 1. Navigate to the profile page 2. Enter some text into the textbox and click the Post button | The text entered should appear at the top of the wall posts | Cory Stone | Passed
Wall posts have timestamp | Wall | No | Logged in |  | 1. Navigate to the profile page 2. Enter some text into the textbox and click the Post button | In the post that appears on the wall, there should be a timestamp with the current time | Cory Stone | Passed
Wall posts appear in order | Wall | No | Logged in |  | 1. Navigate to the profile page 2. Create multiple posts 3. Reload the page | The posts should appear on the wall in order with the newest posts at the top | Cory Stone | Passed
Add wall post to another wall | Wall | Yes | Logged in |  | 1. Navigate to another user's profile page 2. Enter some text into the textbox and click the Post button | The text entered should appear at the top of the wall posts The logged in user's email address should appear with the post | Cory Stone | Passed
Add comment to a wall post | Wall | Yes | Logged in User has posts on wall |  | 1. Navigate to the profile page 2. Enter some text into the textbox under a wall post and click the Comment button | The text entered should appear blow the wall post. The profile picture and first name of the poster should appear with the comment, and should link back to the poster's profile. | Cory Stone | Passed
Comments have timestamp | Wall | No | Logged in User has posts on wall |  | 1. Navigate to the profile page 2. Enter some text into the textbox under a wall post and click the Comment button | In the comment that appears below the wall post, there should be a timestamp with the current time | Cory Stone | Passed
Send friend request | Friends | Yes | Logged in Another user in system who is not friended |  | 1. Navigate to an non-friended user's profile 2. Click Send Friend Request 3. Log in as the non-friended user and view friends list | A friend request with the requesting user's profile picture, first name, and last name, should appear on the non-friended user's friend requests list. The entry should be a link back to the requesting user's profile page. | Cory Stone | Passed
Accept friend request | Friends | Yes | Logged in Another user in the system has sent a friend request |  | 1. Navigate to the friends list 2. Click on the Accept button for a friend request | The requesting user's profile picture, first name, and last name should appear in the friends list, with a link back to the requesting user's profile page. The requested user's profile picture, first name, and last name should appear in the friends list of the requesting user, with a link back to the requested user's profile page. | Cory Stone | Passed
Decline friend request | Friends | No | Logged in Another user in the system has sent a friend request |  | 1. Navigate to the friends list 2. Click on the Deny button for a friend request | The friend request should be removed from the list. No change is made to the requestor or requestee's friends list. | Cory Stone | Passed
View friends list | Friends | Yes | Logged in Have multiple friends in the friends list |  | 1. Navigate to the friends list | The friends' usernames and profile pictures should appear in the friends list | Cory Stone | Passed
Remove friend | Friends | No | Logged in Have a friend in the friends list |  | 1. Navigate to the friends list 2. Click the Remove button under a friend | The friend should be removed from the friends list The logged in user should be removed from the friend's friend list | Cory Stone | Passed
Send message to global chat | Chat | No | Logged in |  | 1. Navigate to the chat 2. Send a message to the chat | The message should appear on the left side of the chat window The message should include the user's profile picture and first name, which link to the user's profile | Cory Stone | Passed
Receive message in global chat | Chat | No | Logged in as two different users in two separate browsers |  | 1. In both browsers, navigate to the chat 2. In one browser, send a message to the chat | The message should appear on the right side of the chat window in the other browser The message should include the profile picture and first name of the user who sent it, which link back to the user's profile | Cory Stone | Passed
Search by first name | Search | Yes | There are multiple users with the same first name |  | 1. Navigate to the search page 2. Select First Name from the dropdown 3. Enter a common first name between multiple users 4. Click search | A results section should appear, showing the profile picture, first name, and last name of each user having the provided first name. Clicking on the picture or name should bring you to that user's profile. | Cory Stone | Passed
Search by last name | Search | No | There are multiple users with the same last name |  | 1. Navigate to the search page 2. Select Last Name from the dropdown 3. Enter a common last name between multiple users 4. Click search | A results section should appear, showing the profile picture, first name, and last name of each user having the provided last name. Clicking on the picture or name should bring you to that user's profile. | Cory Stone | Passed
Search by email | Search | No | There are multiple users with the same email address |  | 1. Navigate to the search page 2. Select Email from the dropdown 3. Enter a common email between multiple users 4. Click search | A results section should appear, showing the profile picture, first name, and last name of each user having the provided email. Clicking on the picture or name should bring you to that user's profile. | Cory Stone | Failed | There is no option to search by email. See https://www.pivotaltracker.com/story/show/144492545
Search by gender | Search | No | There are multiple users with the same gender |  | 1. Navigate to the search page 2. Select Gender from the dropdown 3. Enter a common gender between multiple users 4. Click search | A results section should appear, showing the profile picture, first name, and last name of each user having the provided gender. Clicking on the picture or name should bring you to that user's profile. | Cory Stone | Passed
Search by birth date | Search | No | There are multiple users with the same birth date |  | 1. Navigate to the search page 2. Select Birth Date from the dropdown 3. Enter a common birth date between multiple users 4. Click search | A results section should appear, showing the profile picture, first name, and last name of each user having the provided birth date. Clicking on the picture or name should bring you to that user's profile. | Cory Stone | Passed
Country | Search | No | There are multiple users with the same country |  | 1. Navigate to the search page 2. Select Country from the dropdown 3. Enter a common country between multiple users 4. Click search | A results section should appear, showing the profile picture, first name, and last name of each user having the provided country. Clicking on the picture or name should bring you to that user's profile. | Cory Stone | Passed
Search with no match | Search | No |  |  | 1. Navigate to the search page 2. Select First Name from the dropdown 3. Enter a first name that is not used by anyone in the system 4. Click search | A results section should appear with no data in it. | Cory Stone | Passed
Search with no data | Search | No |  |  | 1. Navigate to the search page 2. Click search | A results section should appear with no data in it. | Cory Stone | Passed