## Arpita Vats
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 (1/20 - 1/26) | 5 |  | 1 | 0- started working on tutorial of java Script | 2
2 (1/27 - 2/2) | 5 |  | 1 | 0- conitnued with java Script | 2
2 (2/3 - 2/9) | 5 |  | 1 | 0- started learning node.js | 2
4 (2/9/ - 2/15)
5 (2/17 - 2/23) | 5 | 7 | 1 | 0-learning angular js and node.js | 3 |  | 1 | 3 |  |  |  |  | 6
6 (2/24 - 3/2) | 4 | 7 | 1 | 3- wokring for about me page using bootstrap 3.workinf on designing of authorization page. | 2 | 3 |  | 3 |  |  |  |  | 8
7 (3/3 - 3/9) | 4 | 7 | 2 | 0- learning animation and dynamic page chnages |  | 1 |  | 3 | 3 |  |  |  | 4
8 (3/10 - 3/16) | 4 | 5 | 0.5 | 3.designingauthorization page |  |  |  | 4.5 | 1
9 (3/17 - 3/23) | 4 | 5 | 3 | 0-Learning angular js for chat feature | 3
10 (3/24 - 3/30) | 4 | 5 | 2

## Nicholas Hattabaugh
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 (1/20 - 1/26) | 5 | 5 | 1 | 0 - research MEAN Stack | 5
2 (1/27 - 2/2) | 7 | 5 | 2 | 3- start project |  |  |  | 5
2 (2/3 - 2/9) | 5 | 3 | 2 | 2-begin designing db models schema and cloud environment 3-more coding |  |  | 1 | 2
4 (2/9/ - 2/15) | 8 | 7 | 2 | 3-adding to existing project code, implementing web-socket into backend |  |  |  | 6
5 (2/17 - 2/23) | 7 | 6 | 1 | research chat deployment research universal socket factory for the front end of the application chat socket configuration
6 (2/24 - 3/2) | 8 | 7 | 1 | chat deployment research, async js research, websockket research Angular and node JS Security
7 (3/3 - 3/9) | 10 | 8 | 2 | merge chat room front end design chat front end controller
8 (3/10 - 3/16) | 9 | 8 | 1 | Socket Event handler instant messaging databse object controller private chat started working on a user search algorithm
9 (3/17 - 3/23) | 8 | 7 | 1 | Socket Event handler instant messaging databse object controller private chat started working on a user search algorithm
10 (3/24 - 3/30) | 7 | 4 | 3 | Teaching team about angular
11 (3/31 - 4/6) | 6 | 3 | 3 | Teaching sub group about anuglar/socketio
12 (4/7 - 4/13) | 5 | 4 | 1 | 0 - Deployment Research 3 - Preparing some application code for deployment
13 (4/14 - 4/20)

## Robert Gomez
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 (1/20 - 1/26) | 6 |  | 1 | 0 - research MEAN Stack | 6 | [6 empty] | 0 | 8
2 (1/27 - 2/2) | 5 |  | 2 | 0 - read tutorials on Node.js and MongoDB | 5 | [6 empty] | 0 | 8
2 (2/3 - 2/9) | 5 |  | 2 | 0 - look through sample project code | 5 | [6 empty] | 0,2 | 8
4 (2/9/ - 2/15) | 6 |  | 2 | 0 - research SCMP and how to write one 2 - write SCMP and get ready for presentation | 2 |  | 4 |  |  |  |  | 2,3 | 10
5 (2/17 - 2/23) | 7 |  | 1 | 2 - decide on how the posts should look on the wall 3 - start writing html code for the posts |  |  | 1 | 5 |  |  |  | 3 | 8
6 (2/24 - 3/2) | 9 |  | 1 | 3 - start writing back end functionality for wall posts |  |  |  | 8 |  |  |  | 3 | 8
7 (3/3 - 3/9) | 9 |  | 2 | 3 - add finishing touches to wall 4 - start testing wall posts to make they're working as expected 6 - get ready for git merge |  |  |  | 5 | 2 |  | 2 | 3,2 | 8
8 (3/10 - 3/16) | 4 |  | 1 | 2 - start looking into how to add comments to a post 3 - work on defect |  |  | 2 | 1 |  |  |  |  | 8
9 (3/17 - 3/23) | 5 | 2 | 3 | 1 - Added users stories to backlog 1 - Backlog grooming and iteration planning with team 3 - start initial coding for Comments |  | 3 |  | 2 |  |  |  | 3 | 8
10 (3/24 - 3/30) | 7 | 7 | 0 | 3 - Add functionality to send a friend Request |  |  |  | 7 |  |  |  | 3 | 8
11 (3/31 - 4/6) | 9 | 6 | 3 | 3 - add functionality to accept friend request and add friend and deny request 5. Meet to plan for presentation and prepare for demo |  |  |  | 6 |  | 3 |  | 3,1 | 8

## Mike Eskowitz
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 (1/19/2017 - 1/25/2017) | 6 | 5 | 1 | 0 - I began going through MEAN tutorials to understand the API and development environments | 5 | 0 | 0 | 0 | 0 | 0 | 0
2 (1/26/2017 - 2/1/2017) | 5 | 4 | 1 | 0 - I continued going through tutorials and brought up a webserver on my Windows machine so that I can run the code | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8
3 (2/2/2017 - 2/8/2017) | 8 | 7 | 1 | 0 - Read up on html and javascript | 1 | 0 | 0 | 6 | 0 | 0 | 0 |  | 8
3 - began implementing the profile options page in the application
4 (2/9/2017 - 2/15/2017) | 8 | 7 | 1 | 0 - read up on node.js | 1 | 0 | 0 | 6 | 0 | 0 | 0 |  | 8
|  |  |  | 3 - began implementing the profile options page in the application | [8 empty] | 8
5 (2/16/2017 - 2/22/2017) | 8 | 7 | 1 | 3 - worked on implementing profile options page in the application | 0 | 0 | 0 | 7 | 0 | 1 | 0 | Implement profile options page | 8
6 (2/23/2017 - 3/1/2017) | 5 | 4 | 1 | 3 - wored on implementing profile options page in the application | 0 | 0 | 0 | 4 | 0 | 1 | 0 | Finish implementation of profile options page | 8
7 (3/2/2017 - 3/8/2017) | 12 | 8 | 4 | 3 - Integrated profile feature with development branch | 1 | 0 | 0 | 7 | 0 | 4 | 0 | Work on presentation and paper | 8
5 - Prepared slides for the presentation
8 (3/9/2017 - 3/15/2017) | 9 | 9 | 4 | 3 - Reviews integration changes to get profile to work | 0 | 0 | 0 | 4 | 1 | 4 | 0 | Begin new feature development | 8
5 - Editted slides and reviewed paper
9 (3/16/2017 - 3/22/2017) | 5 | 4 | 1 | 3 - attempted to merge profile info and wall pages | 0 | 0 | 0 | 4 | 0 | 1 | 0 | Attempt to get backend to produce other user's profile pages | 8
10 (3/23/2017 - 3/29/2017) | 1 | 0 | 1 | Bad week. Didn't have time to do anything so far. | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Attempt to get backend to produce other user's profile pages | 8
11 (3/30/2017 - 4/5/2017) | 18 | 16 | 2 | 0 - Read through documentation regarding route script file | 2 | 0 | 0 | 12 | 2 | 2 | 0 |  | 8
3 - modified routing code to support passing of profile data by performing an http get on api/profile/username
4 - performed iteration 2 regression testing
12 (4/6/2017 - 4/12/2017) | 8 | 3 | 5 | 5 - Worked on slides | 0 | 0 | 0 | 3 | 0 | 5 | 0 | Work on search feature
13 (4/13/2017 - 4/19/2017) | 9 | 8 | 1 | 3 - Started working on search page. Didn't get it to work | 0 | 0 | 0 | 8 | 0 | 0 | 0 | Finish search page | 8
14 (4/20/2017 - 4/26/2017) | 14 | 13 | 1 | 3 - Fixed search page so you can search database from web interface | 2 | 0 | 0 | 11 | 0 | 0 | 0 | None | 0
0 - Read documentation on using regular expressions to query mongo database

## Cory Stone
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 (1/20 - 1/26) | 6 | 5 | 1 | 0 - Reading tutorials, setting up environment, and doing traning exercises for MEAN technology stack 0 - Reading Encounter case studies to prepare topics for team meeting 5 - Discussions with team about course logistics, setting meeting time, etc. | 4.5 |  |  |  |  | 0.5 |  | 0 - Continue learning about MEAN stack 1 - Come up with some desired app features, reference similar apps, so we can draft requirements 1 - Start work on SQAP section of SPPP | 8
2 (1/27 - 2/2) | 5 | 3 | 2 | 0 - Learning about node.js 0 - Run sample project to verify environment setup 1 - Start filling in SPPP with functional requirements | 2 | 1 | [5 empty] | 0 - Continue learning about node.js 1 - Investigate authentication methods for app 1 - Add more details to SPPP 2 - Work on design for authentication | 6
3 (2/3 - 2/9) | 5 | 4 | 1 | 0 - Learning about node.js 1 - Investigating capabilities of node modules to do OAuth with Facebook/Google | 3 | 1 | [5 empty] | 0 - Continue learning about node.js 1 - Finish Requirements section of SPPP 1 - Finish SQAP section of SPPP 2 - Work on design for authentication | 6
4 (2/10 - 2/16) | 8 | 7 | 1 | 0 - Learning about express.js 1 - Finish requirements section of SPPP 1 - Finish SQAP section of SPPP 1 - Add content to iteration 0 presentation 5 - Coordinate with team on SPPP and presentation | 3 | 4 |  |  |  | 1 |  | 0 - Continue learning about node and express.js 1 - Create some user stories for authentication 2 - Work on design for authentication 3 - Start implementation for authentication | 6
5 (2/17 - 2/23) | 8 | 7 | 1 | 0 - Learning about express.js 2 - Working on design for Facebook OAuth 3 - Implementing Facebook OAuth | 3 |  | 1 | 3 |  |  |  | 0 - Continue learning about express.js 1 - Create user stories for OAuth with Facebook, Google 3 - Add unit tests for Authentication modules, give detailed description for team members to follow | 6
6 (2/24 - 3/2) | 9 | 8 | 1 | 0 - Learning about express.js 1 - Requirements analysis for Authentication and Search by email 3 - Adding unit tests for front-end and back-end authentication modules with commentary for team | 2 | 3 |  | 3 |  |  |  | 1 - Add more user stories, meet with team to prioritize 3 - Implement Google OAuth 3 - Work with team to merge features into cohesive experience 4 - Start preparing test plan | 8
7 (3/3 - 3/9) | 9 | 7 | 2 | 1 - Added users stories to backlog 3 - Worked with team to merge everyone's work 4 - Created test plan 4 - Tested features |  | 1 |  | 3 | 3 |  |  | 3 - Implement Google OAuth 4 - Finish all testing for iteration 1 | 4
8 (3/10 - 3/16) | 7 | 5.5 | 1.5 | 3 - Added more unit tests 3 - Implemented Google OAuth 4 - Tested items in test plan 4 - Bug fixes |  |  |  | 4.5 | 1 |  |  | 1 - Add user stories to backlog 1 - Backlog grooming and prioritization 3 - Work on combining profile data and wall posts into single view | 5
9 (3/17 - 3/23) | 6.5 | 3.5 | 3 | 1 - Added users stories to backlog 1 - Backlog grooming and iteration planning with team 3 - Combined the user's profile data and wall posts into a single view |  | 3 |  | 2 |  | 0.5 |  | 3 - Allow users to view other users' profiles 3 - Don't show other users' profiles as editable forms | 5
10 (3/24 - 3/30) | 4.5 | 4.5 | 0 | 3 - Allow users to view other users' profile pages 3 - Add toggle option for making profile info form editable |  |  |  | 4 |  | 0.5 |  | 3 - Don't show other users' profiles as editable forms 3 - Only show wall posts for the profile you are viewing 4 - Update test plan and run regression tests 4 - Collect test results for testing report, include code coverage | 8
11 (3/31 - 4/6) | 14.5 | 13.5 | 1 | 3 - Make wall posts specific to a user, a user's wall posts appear only on their profile 3 - When logged in, navigation link to profile page will add user's id to the url so the correct profile is shown 3 - Users can only edit their own profile 3 - Help with implementation of friends/friend requests 4 - Updated test plan 4 - Tested features |  |  |  | 10 | 2.5 | 1 |  | 3 - Add logout functionality 3 - Show user information on wall posts | 5
12 (4/7 - 4/13) | 4 | 3 | 1 | 3 - Added logout functionality 3 - Started work on showing user information on wall posts |  |  |  | 2.5 |  | 0.5 |  | 3 - Show user information on wall posts 3 - Show user information on chat messages | 5
13 (4/14 - 4/20) | 6.5 | 5.5 | 1 | 3 - Finished work on showing user information on wall posts 3 - Worked on new login page layout 3 - Started work on showing user information on chat messages |  |  |  | 5 |  | 0.5 |  | 3 - Show user infomation on chat messages 3 - Show search results 3 - Fix missing timestamps on wall messages 3 - Fix wall post comments | 10
14 (4/21 - 4/27) | 22 | 20 | 2 | 3 - Integrated picture/name with comments, chate messages, search results 3 - Improved user experience in terms of transition from login to profile and UI design 3 - Lots of stablization and configuration to make the app deployable in locations other than on local system 4 - Lots of testing on deployed product |  |  |  | 15 | 5 |  |  | 6 - Sleep 6 - Study

## Ed Orsini
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 (1/20 - 1/26) | 9 | 8 | 1 | 0 - Learning more about the MEAN stack via tutorials. 5 - Communicating with the team via email & Slack | 6 |  |  |  |  | 2
2 (1/27 - 2/2) | 5.5 | 3 | 2.5 | 0 - Continue to read/learn about MEAN stack. | 2 |  |  |  |  | 1
3 (2/3 - 2/9) | 6 | 5 | 1 | 0 - Continue to read/learn about MEAN stack. | 4 |  |  |  |  | 1
4 (2/10 - 2/16) | 2.5 | 1.5 |  | 1 - Worked on configuration section of the SPPP. |  | 1 |  |  |  | 0.5
5 (2/17 - 2/23) | 6 | 6.5 |  | 0 - Continue to read/learn about MEAN stack. 3 - Worked on implementing the profile picture upload. 5 - Caught up on slack messages. | 3 |  |  | 3 |  | 0.5
6 (2/24 - 3/2) | 15 | 12 | 2 | 0 - started learning about how to upload files using Express 3 - installed Multer module and learned how to use it 3 - worked with team to merge all feature branches to development branch | 4 |  |  | 8 |  | 1
7 (3/3 - 3-9) | 8 | 2 | 6 | 3 - worked with team to merge all feature branches to development branch |  |  |  |  | 1 | 1
8 (3/10 - 3/16) | 16 | 10 | 4 | 0 - watched video posted by Professor regarding Juice 6 - working on content for presentation of iteration 1 (with Mike) 6 - worked on design document | 1 |  |  |  |  | 1
9 (3/17 - 3/23) | 8 | 6 | 1 | 3 - merged feature branches to development branch 3 - worked on "friends" feature - created view and displayed user's friends 4 - testing development branch after merging 6 - met with entire team in order to enter stories for iteration #2, prioritized them, and set up teams to work on them | 1 |  |  | 5 | 0.5 | 1 | 3
10 (3/24 - 3/30) | 6.5 | 5 | 0.5 | 3 - working on deleting a friend 4 - working on unit testing for picture feature and for friends feature |  |  |  | 4 | 0.5 | 0.5
11 (3/31 - 4/6) | 11 | 8 | 1 | 1 - cleaned up user stories to refine requirements and user acceptance tests 3 - worked with team to integrate `request friend` button on wall 4 - worked with team to remove hardcoded references to specific users (that was done while developing/testing) 4 - tested and accepted stories and Pivotal Tracker 6 - met with team to iron out plan for presentation/demo of Iteration #2 6 - started the slides for Iteration #2 demo |  |  |  | 7 | 0.5 | 0.5
12 (4/7 - 4/13) |  | 7 | 1 | 3 - worked on picture upload functionality to stay and refresh the page after upload instead of redirecting to another page 3 - worked on deleting a picture from a user's picture gallery 5 - assigned tasks within subgroup 3 - working on user's picture gallery - ability to only see your pictures |  |  |  | 5 | 0.5 | 0.5
11 (4/14 - 4/20) |  | 5 | 1 | 4 - tested Ravi's branch of assigning a picture to a profile 3 - merged Ravi's branch into the development branch 3 - working on user's picture gallery - ability to only see your pictures |  |  |  | 3 | 0.5 | 0.5
11 (4/21 - 4/27) |  |  |  | 3 - work on limiting file uploads to only image files 3 - work on limiting file sizes when uploading images 3 - gracefully show an error when no file selected, and the submit button is pressed 3 - working on user's picture gallery - ability to only see your pictures 5 - working on slides for final demo

## Ravi K.Rajendran
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 (1/20 - 1/26) | 3 | 2 | 1 | 0- Learning MEAN basics | 2
2 (1/27 - 2/2) | 2 | 1 | 1 | 0- MEAN Tutorials 5- Webex Meeting with team | 1
3 (2/3 - 2/9) | - | - | - | - | - | - | - | - | - | - | -
4 (2/10 - 2/16) | - | - | - | - | - | - | - | - | - | - | -
5 (2/17 - 2/23) | - | - | - | - | - | - | - | - | - | - | -
6 (2/24 - 3/2) | 7 | 5 | 2 | 0- Mongo and Node tutorials 2- Realtime webRTC | 3 |  | 2
7 (3/3 - 3-9) | 11 | 10 | 1 | 0-Express tutorials 3- Implemented a simple chat feature | 4 |  |  | 6
8 (3/10 - 3/16) | 6 | 5 | 1 | 0- Angular tutorials 6- Implemented a server-client data transfer | 2 | [5 empty] | 3
9 (3/17 - 3/23) | 9 | 6 | 3 | 0-Angular directives 3- Implementing one-to-one chatting | 2 |  |  | 4
10 (3/24 - 3/30) | 9 | 6 | 3 | 2- Chat design 3- Implementing chat scroll feature | 2 |  |  | 4
11 (3/31 - 4/6) | 4 | 2 | 2 | 2- Designed the model and controller for the profile picture |  |  | 2
12 (4/7 - 4/13) | 3 | 2 | 1 | 3- Implementing the set-profile picture |  |  |  | 2
13 (4/14 - 4/20)
14 (4/21 - 4/27) | 12 | 9 | 3 | 2-Designed the comments section 3-Implemented the comment section 3-Implemented the posting feature on the wall |  |  | 2 | 7